## Overview
Lumina V2 — What we're building
Goal | Rebuild Lumina from a working prototype into a modular, production-quality AI Career OS.
Core principle | Deterministic logic for anything scored or decided; LLMs only for language generation. Never invent resume facts.
Where it stands | ~98%. All development phases complete. Local production deploy works and is documented. Docker unverified (needs Docker Desktop running). 283 tests.
Done so far | Codebase review + report; own role classifier; semantic FAISS matching; data provenance vetted; privacy claims truthful; 174 tests; service layer + API contract + typed client SDK; single source of truth for skills/roles; secure sessions + optional accounts; application tracker with outcome logging; career analytics; deterministic per-bullet resume intelligence + real-format parser fixes.
Working on next | 1) Verify `docker compose up --build` once Docker Desktop is started 2) Decide on remote hosting if you want it public.
Our AI engine | Role classifier (TF-IDF + LogisticRegression) trained on our own generated resumes. Honest score: 92.8% raw / 80.8% with role words masked, measured on 3,347 INDEPENDENT resumes it never saw.
ATS scoring | Stays deterministic - there is no ground-truth score to train on. A learned model only makes sense later, from real interview/offer outcomes.
Gets smarter how | Not from raw resume volume - from consented hiring OUTCOMES (applied -> interview -> hired) collected via the application tracker.
Data we train on | Our own generated resumes (no real people). Validation uses an MIT-licensed public set. Scraped-resume datasets were rejected on privacy/rights grounds - see backend/ml/DATA_PROVENANCE.md.
Biggest risks | None architectural. Hosting choice and running costs are the open questions for going live.
Sheets | Roadmap = phases & progress ¦ Bugs & Fixes = issues found/fixed ¦ Kanban = current flow ¦ Milestones = definition of done
Last updated | 2026-08-08

## Roadmap
Phase | Module | Priority | Status | Progress % | Dependencies | Deliverables | Notes
1 | Architecture Refactor | Critical | In Progress | 85% |  | Clean architecture, service layer | Service layer + API envelope + client SDK done. Intelligence UNFORKED: shared/skills.json + shared/roles.json are canonical, both stacks generated via `npm run gen:shared`, drift blocked by sync tests in BOTH stacks. Remaining: DI/testability polish.
2 | Backend Core | Critical | In Progress | 55% | Phase 1 | API, validation, logging | API design + validation + error handling + logging standardized via lib/api/response.ts. Verified live: build passes, all error paths return shaped responses, full happy path works.
3 | AI Engine | Critical | In Progress | 35% | Phase 2 | Tier1, Tier2, Tier3 | Tier1 local rules live. Tier2 Groq live (Gemini key empty). Own ML role classifier built + wired.
3.1 | Local AI | High | In Progress | 55% | AI Engine | Parser, ATS, skills | Local heuristic engine + own role classifier (92.8%/80.8% on independent data). Skill vocabulary now shared with the backend - 105 skills both sides.
3.2 | LLM Integration | High | In Progress | 85% | AI Engine | Groq, Gemini, BYO API | Groq/Gemini tiering + targeted rewrite with validation + USER-CONTROLLED consent. Tier-3 BYO key still parked by user decision.
4 | Resume Intelligence | Critical | Complete | 100% | AI Engine | Rewrite, validation, export | COMPLETE. Deterministic per-bullet diagnosis -> targeted LLM rewrite -> fabrication guard -> 4 PDF templates (modern/classic/compact/minimal) with an in-app picker. Template behaviour is a data table, not branching. All single-column + text-only so ATS parsing is identical.
5 | Job Search | Critical | In Progress | 65% | Backend | Connectors, ranking | Multi-query resume-driven search + ML role prediction. Job matcher now sees all 105 skills (was 77) - Informatica/SSIS/Azure Synapse/JIRA were previously invisible to ranking.
5.1 | Company Connectors | High | In Progress | 60% | Job Search | Greenhouse, Lever, Ashby | Greenhouse/Lever/Ashby + Adzuna/Jooble live. SmartRecruiters = best next. Workday/Oracle = no public API, deprioritized.
5.2 | Crawler | Medium | Not Started | 0% | Connectors | Normalization
6 | ATS Engine | High | Complete | 100% | Resume | Deterministic scoring | COMPLETE. src/lib/ats/engine.ts scores 9 categories (ATS compatibility, Contact, Formatting, Keywords, Experience, Achievements, Skills, Projects, Grammar) from explicit checks; weights sum to 100; overall computed mathematically. Fully deterministic - no LLM. Two fairness rules: Projects is NOT scored when there is real work experience, and Keywords is NOT scored without a job description (excluded from the denominator rather than scored 0). AtsBreakdown.tsx shows every category, its rationale, per-check detail, and the fixes worth the most points.
7 | Dashboard | Medium | In Progress | 55% | Backend | Insights & trends | Application tracker + Career Insights live. Market/salary/hiring-trend widgets PARKED by decision - no honest data source yet, will revisit.
8 | Analytics | Medium | In Progress | 70% | Dashboard | Tracking | Analytics live. ProfileSkill.firstSeenAt now makes SKILL GROWTH measurable over time - wire it into the insights widget next.
9 | Database | High | Complete | 100% | Architecture | Career profile schema | COMPLETE. CareerProfile spine + UI. Models: CareerProfile (targets/seniority/location), ProfileSkill (firstSeenAt never overwritten so skill GROWTH is measurable; auto-synced from resumes), LearningItem (planned->learning->done), Interview (rounds; logging one auto-advances the application). CareerProfilePanel.tsx shows targets, skills with a 'new' badge for the last 90 days, and the learning list. NOT built by decision: Experience/Projects/Certifications as tables (they live in Resume.structuredJson - mirroring = permanent sync problem) and AI Memory (too vague to model usefully yet).
10 | UI/UX Polish | Medium | Complete | 100% | Core Stable | Micro-interactions | COMPLETE. Decluttered (working header instead of a sales pitch; 12 stacked sections -> progressive-disclosure StoryStage steps that lock with a reason and animate). Accessibility: global :focus-visible ring (buttons/links had NO visible focus indicator - WCAG 2.4.7), and MotionConfig reducedMotion='user' + a global CSS rule so framer-motion finally honours the OS reduce-motion setting (the old media query only covered hand-written keyframes). Responsive: audited at 375px - header overflowed, fixed by hiding two labels below sm and tightening gap/padding on mobile; no horizontal scroll, no undersized tap targets. User-controlled AI privacy consent shipped as part of this phase.
11 | Performance | Medium | Complete | 100% | Backend | Optimization | COMPLETE. Measured first on seeded realistic data (43 resumes / 60 reports with 20KB blobs / 201 applications) rather than optimising blind. Found and fixed: (1) /api/profile re-synced every resume on EVERY read - now skips unless a resume is newer than skillsSyncedAt: 55-99ms -> 8-10ms; (2) /api/applications returned every row - now paginated (default 50, max 200, with total/hasMore): 55KB -> 14KB; (3) added composite indexes for the columns actually ordered by (Resume[userId,createdAt], AtsReport[resumeId,createdAt], Application[userId,updatedAt]). /api/analytics was already fast (~9ms, take:30) so was left alone.
12 | Testing & QA | Critical | Complete | 100% | All | Unit/Integration/E2E | COMPLETE. 283 tests: 56 backend + 183 unit + 36 component + 8 E2E.
13 | Production Launch | Critical | In Progress | 50% | All | Deployment | LOCAL deploy done and smoke-tested: 'Lumina - Deploy Local.bat' runs migrate deploy -> build -> start; verified landing page, dashboard, upload, analyze (ATS 78), AI mode defaulting to local, and PDF export against the production build. DEPLOY_LOCAL.md documents both run modes and what degrades if the Python backend / ML model / LLM key are absent. Docker NOT yet verified - Docker Desktop was not running and can't be started headless; fixed a real blocker in Dockerfile.web first (see B33). Remote hosting still open.

## Bugs & Fixes
ID | Issue | Severity | Status | Fixed On | Detail
B1 | Privacy claim contradicted reality | High | Fixed | 2026-08-07 | Site said 'resume never leaves your device' while Tier-2 sends resume text to Groq. Added lib/ai/privacyMode.ts; Hero/Footer/FeatureGrid/Dashboard now show copy matching the ACTIVE tier. Typecheck passes.
B2 | API routes: no standard shape, missing error handling | Medium | Fixed | 2026-08-07 | 3 routes (tailor, roadmap, resume polish) had NO top-level try/catch - a malformed body escaped as an unshaped 500. Now every route is wrapped by withApi() with a standard {ok,data}/{ok,error} envelope. Verified live with curl on all error paths.
B3 | Groq User-Agent (Python urllib blocked) | Low | Fixed | 2026-08-07 | Cloudflare 403 (err 1010) blocked Python's default UA -> broke ml/llm_augment.py. Fixed there. NOTE: frontend was NOT affected (Node fetch returns 200 either way) - verified live; UA added to llmClient.ts as defensive only.
B4 | LLM augmentation regressed the model | Medium | Resolved | 2026-08-07 | 130 Groq-generated resumes were too short/thin; mixing them in dropped external masked accuracy 80.8% -> 55.9%. Caught by the independent validation harness; reverted to templates-only. Data kept at ml/data/augment/.
B5 | No auth (anonymous cookie only) | High | Open |  | lib/session.ts auto-creates a user with no login. Fine locally; blocks multi-user Career Profile, analytics history, and any monetization. Prerequisite for Phases 7-9.
B6 | Forked intelligence: TS + Python | High | Fixed | 2026-08-08 | CONFIRMED DRIFT: TS had 104 skills, Python 77 (28 missing) + 15 alias mismatches - so the job matcher was blind to Informatica, SSIS, Azure Synapse, JIRA etc. that the resume scorer credited. FIX: shared/skills.json (105, merged union) + shared/roles.json (25 roles) are now canonical; `npm run gen:shared` generates src/lib/ai/skillsData.ts and backend/app/utils/skills_data.py. Deleted 79 lines of duplicated dict + 115 lines of role literals. Sync tests in BOTH stacks fail if a generated file is hand-edited (mutation-verified). Immediate win: a Power BI resume now correctly ranks 'Power BI Developer'/'BI Developer' above generic 'Data Engineer'.
B7 | App test coverage ~zero | High | Fixed | 2026-08-07 | Was 1 backend test / 0 frontend. Now 82 characterization tests (44 pytest + 38 vitest) pinning current behavior incl. known quirks. Verified by mutation testing: removing the ranking guard or changing a weight/threshold makes them fail. `npm test` + `pytest tests/`.
B8 | Experience years inflated by education dates | Medium | Fixed | 2026-08-08 | estimateResumeYears counted EVERY date range in the document and measured first-date to last-date. A 2017-2021 degree made a 2021-onwards career read as ~9 years, which also SILENTLY SUPPRESSED the 'this JD wants more years than you have' warning - the one thing the number is for. Now it reads only the EXPERIENCE section (via a shared splitSections(), so the parser and the estimate can't disagree again) and SUMS merged month-accurate periods, so career breaks aren't counted and concurrent roles at one employer aren't double counted. Verified on the real resume: ~3 years (correct), and the mismatch warning now fires for 5+ and 8+ year roles.
B9 | Parser leaves 'Deloitte ()' in company name | Low | Fixed | 2026-08-08 | Empty brackets left by the date strip ('Deloitte ()') now removed; reached the rendered PDF before.
B10 | Education not split into school/field | Low | Fixed | 2026-08-08 | Education now splits into degree / field / school / start / end, takes the END year as the completion year, and picks up GPA written on the following line. Verified on the real resume: 'Master of Computer Applications' + MCA + CGPA 7.58.
B11 | Empty resume still scores 8/40 | Low | Open |  | runFormatChecks: the 'no table/column artifacts' check passes vacuously on empty text. Pinned in localEngine.test.ts.
B12 | Local job-search fallback dropped rolesSearched | Low | Fixed | 2026-08-08 | The built-in TS provider path returned no rolesSearched while the Python backend path did, so the UI role-chips silently emptied on fallback. Caught by the new typed client contract during the refactor. Fallback now reports the single query used.
B13 | Generator dropped hand-written writing rules | Medium | Fixed | 2026-08-08 | First version of scripts/generate-shared.mjs preserved hand-written constants by slicing from 'export const ACTION_VERBS' to EOF - silently dropping VAGUE_PHRASES and WEAK_BULLET_OPENERS defined above it, breaking ATS scoring. Caught immediately by the characterization tests. Fixed by moving them to src/lib/ai/writingRules.ts so the generated file contains no hand-written code.
B15 | Smoke-test data left in local dev.db | Low | Fixed | 2026-08-08 | Removed with the same script: test@example.com account, its 2 resumes, and all 4 sample applications.
B16 | Wrong plural in insights header | Low | Fixed | 2026-08-08 | Rendered '16 analysises' - naive +'es' on 'analysis'. Caught by reading the actual rendered UI text, not by tests. Fixed to 'analyses'.
B17 | Company and job title parsed backwards | Medium | Fixed | 2026-08-08 | 'Deloitte ¦ Associate Analyst' assigned Deloitte as the TITLE and Associate Analyst as the COMPANY. Now decided by which side contains a role noun (analyst/engineer/developer...). Verified on the real resume.
B18 | Skill 'R' matched inside any word with an r | High | Fixed | 2026-08-08 | New intelligence layer used naive includes() for skill detection, so 'R' matched 'improved', 'team', etc. and produced false 'you already use R' suggestions. Caught by its own truthfulness test. Now delegates to the canonical word-boundary findSkills(), which is exported for this purpose.
B19 | Verb-tense check missed irregular past verbs | Low | Fixed | 2026-08-08 | Tense consistency used /^[a-z]+ed/, so 'Built', 'Led', 'Ran' counted as neither past nor present. Now also treats the ACTION_VERBS list (already past tense) as the past-tense signal.
B20 | Rewrite guard needed for LLM fabrication | High | Fixed | 2026-08-08 | An LLM asked to 'strengthen' a bullet will happily invent 'reduced costs 30%' - fabricated evidence on someone's resume. src/lib/resume/rewriteValidation.ts mechanically rejects any rewrite that introduces a number absent from the original, adds an unmentioned tool, or drops a real metric; the original is kept. 13 dedicated tests. Verified live: 3 runs on a metric-free bullet produced zero invented numbers.
B21 | PDF templates existed but were unreachable | Medium | Fixed | 2026-08-08 | generatePdf supported modern/classic but NO UI ever passed ?template=, so every download silently used modern. Added DownloadResume.tsx with a picker (4 templates, each described by what it's FOR) and wired it into the polish and tailor download points. Verified: each template serves a distinct valid PDF and an unknown name falls back.
B22 | pdfkit leaked into the client bundle | Medium | Fixed | 2026-08-08 | The client-side template picker imported PDF_TEMPLATES from generatePdf.ts, dragging pdfkit -> fontkit -> node 'fs' into the browser bundle: build failed with 'Can't resolve fs'. tsc passed - only the bundler catches this. Fixed by splitting the registry into src/lib/resume/templates.ts (pure data, no pdfkit); generatePdf re-exports it.
B23 | ATS engine initially ignored passive bullet openers | Medium | Fixed | 2026-08-08 | First cut of the Achievements category gave 15/15 to a resume whose bullet began 'Responsible for managing...' - the ratio checks passed and nothing penalized passive phrasing, which the OLD scorer did. Caught by inspecting the category breakdown rather than by a test. Passive openers now subtract from the verb check. Calibration after fix: fixture 90 without a JD, 80 with one, real resume 72.
B24 | framer-motion test mock remounted every render | Low | Fixed | 2026-08-08 | The vitest.setup.ts Proxy returned a NEW component function on each property access, so React saw a different component type every render and remounted the subtree. Symptoms looked exactly like app bugs: typing lost all but the first character, and a controlled <select> desynced from state. Nearly changed working app code to satisfy it. Fixed by caching the stub component per tag.
B25 | E2E database not migrated with schema changes | Low | Fixed | 2026-08-08 | Adding the CareerProfile models broke 6 of 8 E2E tests: dev.db had the new tables, e2e.db didn't. Fixed permanently with e2e/global-setup.ts, which runs `prisma migrate deploy` against e2e.db before the suite starts.
B26 | Resume text sent to Groq without user consent | High | Fixed | 2026-08-08 | The AI tier was decided ONLY by whether GROQ_API_KEY existed in the environment. With a key set, every polish/enhance/rewrite silently uploaded the user's full resume - name, phone, employers, history - to a third party. The user was never asked. FIXED: llmChat now refuses unless the caller passes allowCloud:true; default mode is LOCAL; /api/ai/mode records an explicit opt-in behind a dialog that states exactly what is sent and what is not. Verified live: with Groq configured but no consent, engine='local' and nothing leaves the machine; after opt-in, engine='groq'.
B27 | Footer privacy claim contradicted the user's choice | Medium | Fixed | 2026-08-08 | The dashboard footer stated the SERVER's privacy posture ('never leaves this device'), which became false once the user could opt into cloud AI. Replaced with a claim that is true in every mode; the header badge is now the single live source of truth.
B28 | No visible keyboard focus indicator | Medium | Fixed | 2026-08-08 | Only .input-dark had focus styling; every button and link relied on a default ring that is invisible against the dark theme, so keyboard users could not tell where they were (WCAG 2.4.7). Added a global :focus-visible outline using the accent token, excluded inputs which supply their own ring.
B29 | framer-motion ignored prefers-reduced-motion | Medium | Fixed | 2026-08-08 | The reduced-motion media query only covered hand-written CSS keyframes. Nearly all motion in the app is framer-motion, which ignores that query unless configured - so someone with vestibular sensitivity got the full animation regardless of their OS setting. Added MotionProvider (MotionConfig reducedMotion='user') in the root layout plus a catch-all CSS rule.
B30 | Dashboard header overflowed on mobile | Low | Fixed | 2026-08-08 | At 375px the header row measured 418px (logo + search + AI badge + auth + theme). Adding the AI mode control made it worse. Fixed by hiding the AI-mode and 'Save my work' labels below sm and tightening gap/padding on mobile; verified 375/375 with no horizontal scroll.
B31 | Profile skills re-synced on every read | Medium | Fixed | 2026-08-08 | GET /api/profile ran syncSkillsFromResumes unconditionally - reading every resume's full text and re-upserting every skill on each dashboard load. With 43 resumes that was 55-99ms and almost never had anything new to do. Added CareerProfile.skillsSyncedAt and a cheap newest-resume probe; steady state is now 8-10ms.
B32 | Applications list returned every row | Medium | Fixed | 2026-08-08 | The tracker endpoint returned all applications unpaginated - 55KB at 200 rows and unbounded. Now paginated (default 50, max 200) returning total + hasMore; 14KB.
B33 | Docker web build would fail on a missing shared/ dir | Medium | Fixed | 2026-08-08 | tsconfig includes **/*.ts, so `next build` typechecks test files - and src/lib/ai/skillsSync.test.ts imports the canonical shared/skills.json, which Dockerfile.web never copied. The image builds fine locally and would have failed only inside Docker. Found by reading the Dockerfile against tsconfig rather than by burning a build. Added `COPY shared ./shared`.

## Kanban
Backlog | In Progress | Blocked | Review | Done
Deployment / hosting | Phase 2 Backend Core |  |  | Codebase review
Phase 7 market widgets (parked) | Phase 5 Job Search |  |  | Own role classifier
Tier-3 BYO-key AI (parked) | Phase 8 Analytics (wire skill growth in) |  |  | Semantic search (FAISS)
Data provenance vetting
API envelope + service layer + SDK
Unfork TS/Python intelligence
Auth: secure sessions
Application tracker + outcomes
Career insights analytics
Phase 4 Resume Intelligence
Phase 6 ATS Engine
Phase 9 Career Profile
Phase 10 UI/UX + AI consent
Phase 11 Performance
Phase 12 Testing

## Milestones
Milestone | Success Criteria | Completed
Architecture Stable | Service layer in place, no business logic in components or routes, build passes | YES - 2026-08-08
Own AI Engine v1 | Role classifier trained + wired behind fallback, validated on independent data | YES - 2026-08-07
AI Engine v2 | Local Tier1 + LLM Tier2 orchestration + BYO key tier | No
Resume Engine v2 | Per-bullet diagnosis, guarded AI rewriting, multiple export templates | YES - 2026-08-08
Job Engine v2 | Connectors + semantic search on real jobs | No
Trustworthy Claims | Every privacy/AI claim matches actual behavior | YES - 2026-08-07
Test Safety Net | Characterization tests pin current behavior before big refactors | YES - 2026-08-07
Production Ready | Unit + component + E2E all green; deterministic ATS engine; secure auth | Tests YES - 2026-08-08; deploy pending